## Group7_EstimatedEffort
Transportation Logistics Systems & Cayman Express | [6 empty] | Brian | Noor | Paul | Zach
|  |  | Role | Owner | Estimated by Task | Actual by Task | Actual by Task | Actual by Task | Actual by Task | Actual by Task
Preliminary & Parallel Tasks
| Architecture |  |  |  | 12 | 6
|  | Design architecture | Project Manager | Zach | 12 | 6 | 1 | 1 | 1 | 3
| Requirements |  |  |  | 9 | 10
|  | Gather | Requirements Engineer | Paul, Zach | 2 | 5 | 0 | 1 | 2 | 2
|  | Analyze | Requirements Engineer | Paul, Zach | 4 | 4 | 1 | 1 | 1 | 1
|  | Specify | Requirements Engineer | Paul, Zach | 3 | 1 | 0 |  |  | 1
| Documentation |  |  |  | 28 | 5.5
|  | Project Charter | Project Manager | Paul, Zach | 2 | 0 | 0
|  | Release Plan | Project Manager | Paul, Zach | 2 | 0.5 | 0 |  |  | 0.5
|  | Requirements Document | Project Manager, Requirements Engineer | Paul, Zach | 5 | 3 | 1 |  | 1 | 1
|  | Project Plan | Project Manager, Developers | Brian, Noor, Paul, Zach | 5 | 2 | 0 |  | 1 | 1
|  | Architecture Document | Architect | Brian, Noor | 4 | 0 | 0 |  |  | 0
|  | Test Report | Tester | Noor, Brian | 8 | 0 | 0
|  | User Guide & System Admin Doc | Developers, Requirements Engineer | Brian, Noor, Paul, Zach | 2 | 0 | 0
Iteration 1
| Development |  |  |  | 34 | 23
|  | Determine technology needs | Developers | Brian, Noor, Paul, Zach | 1 | 1 | 0 |  |  | 1
|  | Research and learn new language and environment: HTML, CSS, PHP, SQL, WordPress | Developers | Brian, Noor, Paul, Zach | 20 | 7 | 1 | 1 | 1 | 4
|  | Set up development server software | Developers | Brian, Noor, Paul, Zach | 3 | 5 | 1 |  |  | 4
|  | Create and implement source control (GitHub) | Developers | Brian, Noor, Paul, Zach | 2 | 3 | 0 |  | 2 | 1
|  | Unit testing | Developers | Brian, Noor, Paul, Zach | 2 | 0 | 0
|  | Site map | Developers | Brian, Noor, Paul, Zach | 3 | 2 | 0 | 1 |  | 1
|  | WordPress Installation | Developers | Brian, Noor, Paul, Zach | 1 | 3 | 1 |  |  | 2
|  | Website Structure | Developers | Brian, Noor, Paul, Zach | 2 | 2 | 0 |  |  | 2
Iteration 2
| Development |  |  |  | 8.5 | 7.25
|  | Remove "Powered by WordPress" | Developers | Zach | 0.5 | 0.25 |  |  |  | 0.25
|  | SEO Plugin installed & configured | Developers | Zach | 1 | 1.5 |  |  |  | 1.5
|  | Copy content from existing website to WordPress | Developers | Brian, Paul | 2 | 3 | 3 |  | 1
|  | Site prototype | Developers | Zach, Brian | 2 | 2.5 |  |  |  | 2.5
|  | Modify content for SEO purposes | Developers | Noor, Paul | 1 | 0
|  | Update content to be more engaging/compelling | Developers | Noor, Zach | 2 | 0
Iteration 3:
| Development |  |  |  | 24 | 8.5
|  | Color scheme | Developers | Zach | 2 | 0.5 |  |  |  | 0.5
|  | Responsiveness test | Developers | Brian | 1 | 0.5 | 0.5
|  | Test multiple device types | Developers | Brian | 1 | 0.5 | 0.5
|  | Photographs/Compass rose wallpaper | Developers | Brian, Noor, Paul, Zach | 2 | 2.25 |  |  |  | 2.25
|  | Final polish | Developers | Brian, Noor, Paul, Zach | 4 | 1 |  |  |  | 1
|  | Refactor absolutely anything | Developers | Brian, Noor, Paul, Zach | 5 | 0
|  | Finalize content | Developers | Brian, Noor, Paul, Zach | 5 | 2 |  |  |  | 2
|  | Meet with client to discuss finishing details | Developers | Brian, Noor, Paul, Zach | 3 | 0.75 |  |  |  | 0.75
|  | Deliver IP to client | Developers | Brian, Noor, Paul, Zach | 1 | 1 |  |  |  | 1
Total |  |  |  |  | 115.5 | 60.25 | 10 | 5 | 10 | 36.25